ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	3

2.2.	Specific objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	4

3.1.	Assumptions underlying the project	4

3.2.	Risks	4

4.	SCOPE OF THE WORK	4

4.1.	General	4

4.2.	Specific work	4

4.3.	Project management	5

5.	LOGISTICS AND TIMING	5

5.1.	Location	5

5.2.	Start date & period of implementation of tasks	5

6.	REQUIREMENTS	5

6.1.	Personnel	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

BACKGROUND INFORMATION

Partner country

< Albania >

Contracting authority

<NGO Diagnosis>

Country background

< Albania struggles with medical workforce shortages, fragmented healthcare infrastructure, and geographical barriers, leading to delays in urgent care delivery. These challenges are exacerbated by aging populations, the rise of chronic diseases, and gaps in digital health adoption, further limiting healthcare accessibility.

The project responds to these common territorial challenges by addressing healthcare gaps in remote area of Foiniki, aiming to develop and implement a real-time data system that enhances healthcare resilience and emergency response by leveraging advanced digital technologies and innovative medical solutions, train personnel with the necessary skills on performing those tasks and ensuring long-term use of the project’s outcomes.

The initiative includes the deployment of smart medical infrastructure, integrating IoT-enabled medical devices and sensor networks to monitor and manage health data effectively. AI-driven decision support systems will be implemented, utilizing machine learning algorithms for predictive analytics to assist healthcare professionals in critical decision-making. A secure, interoperable platform will be established to facilitate real-time data exchange among healthcare providers, emergency responders, and public health authorities. Additionally, the project will introduce telemedicine and remote monitoring solutions to improve healthcare accessibility, particularly in remote or underserved areas. Specialized training programs will be organized to enhance the skills of healthcare personnel in handling advanced technologies and emergency situations. The adoption of energy-efficient and scalable technologies will ensure the long-term viability and adaptability of the system to different healthcare environments. By integrating these innovative solutions, the project is expected to strengthen healthcare systems, improve response times in emergencies, and enhance overall public health resilience.

The outputs developed by the project will be integrated into daily operations in different rural areas>.

Current situation in the sector

< There are critical healthcare disparities in the cross-border region between Greece and Albania, where rural and remote communities face limited access to primary and emergency medical care and sectoral, infrastructure and geographical barriers lead to delays in urgent care delivery. Therefore, rural and remote areas represent underserved populations with significant healthcare disparities, making them ideal for targeted interventions.

As an organization, NGO Diagnosis supports public awareness, training and healthcare delivery in remote and rural villages. It is dedicated to provide healthcare to vulnerable populations in rural areas in cooperation with relevant municipalities and local legislation.>

Related programmes and other donor activities

< N/A >

OBJECTIVES & EXPECTED OUTPUTS

Overall objective

The overall objective (Impact) to which this action contributes is :

The Project “Minority Inclusive Medical Outreach for Remote Mountainous Areas in Greece and Albania’’, with the Acronym ‘’ MINOR-MED’’ aims to enhance healthcare resilience and emergency response in Greece and Albania by leveraging advanced digital technologies and innovative medical solutions through real-time data collection analysis, and decision making to improve healthcare services and crisis management.

The Project will deploy smart medical infrastructure, integrating IoT-enabled medical devices and sensor networks to monitor and manage health data effectively and will introduce telemedicine and remote monitoring solutions to improve healthcare accessibility, particularly in remote or underserved areas.

Specific objective(s)

The specific objectives (Outcomes) of this contract are as follows:

- Contribute to the creation of an interoperable digital platform for real-time data exchange among healthcare professionals, emergency responders, and public health authorities (D3.1, D3.3, D3.4, D3.5).

- Improve healthcare accessibility through medical visits and consultations (D4.1, 4.2).

- Implement specialized training, equip healthcare personnel with the necessary skills (D4.3, D4.4).

- Provide scalable solutions and ensure long-term impact (D5.1, D5.2, D5.3).

Expected outputs to be achieved by the contractor

The service will be paid on the basis of the delivery of the specified output(s). Payments might be totally or partially withheld if the contractual result(s) have not been reached in conformity with the detailed terms of reference. Payment(s) is/are based on the approval of this/these deliverable(s). Partial payment has to be determined according to the partial implementation of the output(s).

The expected outputs of this contract are as follows:

| Outputs | Title |
| --- | --- |
| 1.2 | Administrative Management Activities – Project Meetings Reports |
| 1.3 | Technical Management Activities, Progress Reports |
| 1.4 | Financial Management Activities – Auditing, Financial Reports |
| 2.2 | Support of the content delivered at the workshop organised by PB2 in Foiniki |
| 2.3 | Organization and Moderation of 2 meetings |
| 2.4 | Organizing local dissemination and knowledge exchange event in the Municipality of Foiniki. |
| 3.1 | Assessment report for the technical specifications of the required medical equipment |
| 3.3 | Report with the on-site technical support for the configuration and installation of telemedicine equipment in rural healthcare facilities |
| 3.4 | Report with key actions undertaken for analyzing functional requirements based on local clinical workflows, adapt system features (e.g., interface, language, user roles) to suit rural healthcare operations, configure modules for appointment scheduling, patient records, and diagnostics, conduct testing and validate functionality with end users. |
| 3.5 | Technical validation and testing report with recommendations for optimization of the telemedicine platform |
| 4.1 | 15 Specialized Medical Visits with local population |
| 4.2 | 10 Face-to-Face Consultations with local population |
| 4.3 | Report with the contribution on the training sessions organised by LB and on informing local professionals |
| 4.4. | Report with the contribution on collection of feedback from the training sessions |
| 5.1 | Financial and Strategic Sustainability Plan |
| 5.2 | Long-term Impact Assessment Report |
| 5.3 | Development of protocols for integrating telemedicine into regional healthcare frameworks |

ASSUMPTIONS & RISKS

Assumptions underlying the project

The main assumptions underlying the project are the following:

- The maturity of the project activities is at satisfactory level. Sufficient capacity of the involved stakeholders and target groups to participate in the project events/activities.

- Existing / Previous data and technical services in general will be available.

- Previous studies including reports, planning activities, financial and economic incentives, methods of analysis of the Health Sector in the Foiniki area, the general regional area and country level will be available.

- The project’s activities will be in line with the needs of the stakeholders involved and political support will facilitate the integration of this in the concerned areas.

Risks

| Risk | Weight | Probability of occurrence | Mitigation measure |
| --- | --- | --- | --- |
| Inability to elaborate the necessary communication means as requested in by the Contract. | High | Low | The contractor is requested to have experience in EU projects. |
| Low capacity of the region and the country to implement the proposed measures-activities. | High | Low | Strong political commitment is in place to meet the sustainable development requirements and impose the necessary measures. |
| Low capacity of the involved stakeholders and target groups to participate in the project activities / events. | Medium | Medium | The invitation approach / the communication channels and the agenda of the events will be redesigned. New dates will be chosen, if necessary, to address the requirements of most stakeholders. |
| Possible delays in project implementation | Medium | Medium | The project timetable will be re-designed, if necessary. A prolongation request will be submitted in case of major delays. |

SCOPE OF THE WORK

General

Description of the assignment

< The scope of the assignment is to provide integrated consulting support to the Contracting Authority for the implementation of the project deliverables listed in section 4.2. >

Geographical area to be covered

< Albania, Foiniki Municipality and nearby remote villages>

Target groups

The project's main target groups are:

- Local communities (especially residents of remote and underserved areas),

- people with disabilities,

- healthcare providers,

- policymakers, and

- EU stakeholders in Greece and Albania.

Specific work

LOT 1 – Project Management and technical services

| Del. | Title | Description | Deadline |
| --- | --- | --- | --- |
| 1.2 | Administrative Management | Provisions of external expertise services for the support of all administrative activities. | Up to 13/02/2028 |
| 1.3 | Technical Management | Provisions of external expertise services for the support of the technical management of the project including consultancy on platform design, system architecture, or other specialized technical areas. | Up to 13/02/2028 |
| 1.4 | Financial Management | Provisions of external expertise services to provide specialized financial services, such as auditing, financial consultancy, and assistance in preparing financial reports. | Up to 13/02/2028 |
| 3.1 | Technical Requirements and System Configuration | Provision of external expertise services to contributing to the assessment of the technical characteristics of the required equipment conduction by evaluating compatibility with the infrastructure and needs of rural clinics, by verifying compliance with relevant healthcare industry standards and certifications, by recommending equipment options that balance functionality, durability, and cost-effectiveness and by identifying potential technical risks and proposing mitigation measures. | Up to 13/02/2028 |
| 3.3 | Development of Telemedicine Platform and Data Management System | Assistance with the installation and configuration of new systems in the rural healthcare facilities including on site-system setup, network configuration, security checks, functionality testing and troubleshooting to ensure the equipment is set up correctly and functions as required. | Up to 13/02/2028 |
| 3.4 | Testing and Validation | Provisions of external expertise services for the support of platform configuration and ensuring that the system aligns with the local healthcare requirements, including analysing functional requirements based on local clinical workflows, adapting system features, configuring modules for appointment scheduling, patient records, and diagnostics, conducting testing and validate functionality with end users. | Up to 13/02/2028 |
| 3.5 | Integration with Healthcare Systems | Provisions of external expertise services for the contribution on testing, validation of the equipment and telemedicine platform including conducting technical performance tests on the telemedicine platform, validating hardware-software interoperability, assessing data protection, uptime, and user accessibility, producing a technical validation report with recommendations for optimization. | Up to 13/02/2028 |
| 4.3 | Capacity-Building Training Sessions | Provisions of external expertise services to support the training sessions in specialized medical areas. The training session organised by LB will involve 35 healthcare professionals from the Municipality of Foiniki. The contractor will ensure that local professionals are adequately informed for the training and can use the system effectively, promoting sustainability and patient safety. | Up to 13/02/2028 |
| 4.4 | Monitoring and Evaluation of Training Impact | Provisions of external expertise services for the assistance in collecting and analysing feedback on project implementation to ensure accurate evaluation and the development of data-driven improvement strategies | Up to 13/02/2028 |
| 5.1 | Sustainability Plan Development | Provisions of external expertise services to develop financial and strategic sustainability plans and to ensure the long-term viability of the telemedicine initiative by developing a financial sustainability plan outlining potential funding sources (e.g., public budgets, cross-border health cooperation), by designing a strategic roadmap for integrating the system into local and national healthcare frameworks, by identifying operational models for long-term service provision and maintenance and by delivering a comprehensive report with concrete recommendations for institutional adoption. | Up to 31/08/2027 |
| 5.2 | Monitoring and Evaluation | Provisions of external expertise services for the support of engaging evaluation specialists to assess long-term impact and propose adjustments by conducting a summative evaluation focusing on healthcare outcomes, service accessibility, and stakeholder engagement, by analysing quantitative and qualitative data (e.g., usage rates, patient satisfaction, institutional uptake), by proposing evidence-based adjustments to enhance sustainability and scalability and by delivering an impact assessment report with strategic recommendations for policy integration and future expansion. | Up to 31/08/2027 |
| 5.3 | Scaling Up Strategies | Provisions of external expertise services for the development of protocols for integrating telemedicine into regional healthcare frameworks to support the institutional adoption of telemedicine services within regional healthcare systems, by analysing current regional healthcare workflows and infrastructure, by aligning the protocols with national health policies, data protection regulations, and clinical standards and by producing a practical implementation guide for healthcare providers and administrators. | Up to 31/08/2027 |

LOT 2 - Communication and dissemination services

| Del. | Title | Description | Deadline |
| --- | --- | --- | --- |
| 2.2 | Organization of Training Workshops | Provisions of external expertise services for the support of the content delivered at the workshop organised by PB2 in Foiniki by tailoring materials to the specific needs of healthcare professionals in rural and underserved areas, by incorporating the latest clinical guidelines and telemedicine best practices, by developing interactive modules and practical case studies to improve engagement and knowledge retention and by providing feedback and recommendations to continuously improve workshop effectiveness. | Up to 13/02/2028 |
| 2.3 | Stakeholder Engagement and Media Outreach | Provisions of external expertise services for the support in stakeholder engagement and project coordination. The contractor will organize and moderate 2 meetings with local stakeholders, guiding discussions to align project objectives with community needs, encourage active participation, resolve potential issues and cover any external professional costs (such as healthcare experts or consultants). | Up to 13/02/2028 |
| 2.4 | Organization of Dissemination and Knowledge Exchange Events | Provisions of external expertise services for the support of organizing local dissemination and knowledge exchange event in the Municipality of Foiniki. The event is expected to host 60 participants, including local stakeholders, municipal staff, community health actors, and media representatives. External expert facilitation and event support (includes coordination with local actors, moderation, preparation of materials). | Up to 13/02/2028 |

LOT3 - Organization of medical visits

| Del. | Title | Description | Deadline |
| --- | --- | --- | --- |
| 4.1 | Scheduling of Specialized Medical Visits | Provision for conduction of 15 visits for routine health assessments to remote villages in the Municipality of Foiniki by medical staff members. Each of the 15 planned visits will be carried out by a mobile team of 3 professionals (2 doctors, 1 nurse) and involves a full-day deployment (including preparation, travel, medical service, and follow-up). Services include physical exams, diagnostics, data entry in the telemedicine platform, health counselling, and patient referrals. | Up to 13/02/2028 |
| 4.2 | Facilitation of Face-to-Face Consultations | Provision for the conduction of 10 targeted follow-up individualized, home-based consultations / visits in remote villages to patients with identified complex health needs based on data collected during Deliverable 4.1. Each visit includes 2 specialized physicians (e.g. cardiologist, neurologist, dermatologist) delivering one-on-one examinations, diagnostic procedures (e.g. ultrasound, ECG), treatment planning, and referrals. | Up to 13/02/2028 |

Project management

Responsible body

NGO Diagnosis, non-governmental organization located in Gjirokaster, Albania.

Management structure

< NGO diagnosis is a non-governmental organization based in Girokaster and has experience in serving vulnerable populations, supporting public engagement, healthcare delivery, and training to improve medical services. It operates in the healthcare sector and in the past had been focused on aiding the elderly residents of specific remote areas in Albania in cooperation with the relevant municipalities.>

Facilities to be provided by the contracting authority and/or other parties

< N/A >

LOGISTICS AND TIMING

Location

Albania / Foiniki Municipality and nearby remote villages.

Start date & period of implementation of tasks

The intended start date is <14/09/2026> and the period of implementation of the contract will be <17> months from this date. Please see point 3 of the main conditions for the actual start date and period of implementation.

REQUIREMENTS

Personnel

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be able to provide input as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well on any potential interference or conflict of interest of the proposed expert in his/her function as expert and his/her present or previous functions working as civil servant. Moreover, proof should be submitted that the expert is seconded or on personal leave.

The selection procedures used by the contractor to select the experts who provide input to the contract must be transparent, must guarantee the absence of professional conflicting interests and the absence of any discrimination based on former or current nationality, gender, place of residence, or any other ground. The findings of the selection panel must be recorded.

[The Organisation & Methodology must include a paragraph demonstrating that a gender sensitive experts’ selection procedure has been applied]

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

Experts

Key experts are not required

The Organisation and Methodology should demonstrate how the contract will comply with these requirements to accomplish the desired output(s). The Organisation and Methodology may include the name of an expert and his profile. Compliance (yes/no answer) of the team (as a whole) with the requirements will be checked, but there will be no marks given to the experts.

Support facilities & backstopping

The costs for support facilities, including backstopping, are included in the tenderer's financial offer.

Office accommodation

Office accommodation for each expert providing input to the contract is to be provided by [the contractor].

Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

REPORTS

Reporting requirements

The contractor will submit the following reports in <English> in one original and one copy:

- Inception Report of maximum 12 pages to be produced after one month from the start of implementation. In the report the contractor shall describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The contractor should proceed with his/her work unless the contracting authority sends comments on the inception report.

Draft final report of maximum <15> pages (main text, excluding annexes). This report shall be submitted no later than one month before the end of the period of implementation of tasks.

Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 15 days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision on Minority Inclusive Medical Outreach for Remote Mountainous Areas. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

MONITORING AND EVALUATION

Definition of indicators

< No special requirements are envisaged >

Special requirements

< No special requirements are envisaged>

* * *

Note that gender balance refers not only to numerical parity, but also to the level of employment and remuneration, roles and functions.